AI/ML ENGINEER

MASTER ROADMAP — FINAL

1 June 2026 → 31 December 2026  |  214 Days  |  16 Phases

Sky (Sahil) — BTech CSE, 3rd Year

This document is LOCKED. No further roadmap rebuilds.

# Phase Overview & Progress Tracker

| Phase | Title | Days | Dates | Status |
| --- | --- | --- | --- | --- |
| 01 | Foundation — Tooling, Python, EDA | Day 001-015 | 01 Jun 2026 - 15 Jun 2026 | COMPLETED |
| 02 | Regression + Deployment | Day 016-029 | 16 Jun 2026 - 29 Jun 2026 | COMPLETED |
| 03 | Classification Foundations + Logging/Pytest | Day 030-044 | 30 Jun 2026 - 14 Jul 2026 | ACTIVE |
| 04 | Advanced Preprocessing + Core Classifiers | Day 045-060 | 15 Jul 2026 - 30 Jul 2026 | UPCOMING |
| 05 | Ensembles, Boosting & Unsupervised Learning | Day 061-082 | 31 Jul 2026 - 21 Aug 2026 | UPCOMING |
| 06 | Model Optimization + FastAPI Deployment | Day 083-095 | 22 Aug 2026 - 03 Sept 2026 | UPCOMING |
| 07 | Deep Learning Fundamentals + PyTorch | Day 096-112 | 04 Sept 2026 - 20 Sept 2026 | UPCOMING |
| 08 | Computer Vision — CNNs & OpenCV | Day 113-128 | 21 Sept 2026 - 06 Oct 2026 | UPCOMING |
| 09 | NLP & Sequence Models | Day 129-143 | 07 Oct 2026 - 21 Oct 2026 | UPCOMING |
| 10 | Transformers, LLMs, RAG & Agents | Day 144-159 | 22 Oct 2026 - 06 Nov 2026 | UPCOMING |
| 11 | React / Web Frontend | Day 160-168 | 07 Nov 2026 - 15 Nov 2026 | UPCOMING |
| 12 | Full-Stack AI Integration | Day 169-175 | 16 Nov 2026 - 22 Nov 2026 | UPCOMING |
| 13 | MLOps & Production Pipelines | Day 176-187 | 23 Nov 2026 - 04 Dec 2026 | UPCOMING |
| 14 | Capstone Development | Day 188-201 | 05 Dec 2026 - 18 Dec 2026 | UPCOMING |
| 15 | Job Readiness & Portfolio | Day 202-212 | 19 Dec 2026 - 29 Dec 2026 | UPCOMING |
| 16 | Final Review | Day 213-214 | 30 Dec 2026 - 31 Dec 2026 | UPCOMING |

# Current Status (as of 1 July 2026)

✅ Completed: Phase 1 (Foundation) — Days 1-15

✅ Completed: Phase 2 (Regression + Deployment) — Days 16-29

✅ Completed: Day 30 (Classification Project Architecture & Logging)

🔴 ACTIVE: Day 31 — Pipeline Verification with Pytest (start today)

📌 Note: Logistic Regression theory & math notation already understood — continue into Day 32 onward.

# PHASE 01: FOUNDATION — TOOLING, PYTHON, EDA

Day 001 - Day 015  |  01 Jun 2026 - 15 Jun 2026  |  Status: COMPLETED

| Day | Date | Topic | Status |
| --- | --- | --- | --- |
| 001 | 01 Jun 2026 | Environment Setup (Anaconda, Jupyter, VS Code, pip/conda) | Completed |
| 002 | 02 Jun 2026 | Python Core Refresher — Variables, Loops, Functions | Completed |
| 003 | 03 Jun 2026 | Python OOP — Classes, Inheritance, Polymorphism | Completed |
| 004 | 04 Jun 2026 | File Handling & Exception Handling | Completed |
| 005 | 05 Jun 2026 | Comprehensions, Lambda, Map/Filter, Decorators | Completed |
| 006 | 06 Jun 2026 | NumPy Fundamentals — Arrays, Broadcasting | Completed |
| 007 | 07 Jun 2026 | NumPy Advanced — Reshaping, Linear Algebra Ops | Completed |
| 008 | 08 Jun 2026 | Pandas — Series & DataFrame Basics | Completed |
| 009 | 09 Jun 2026 | Pandas — Indexing (loc/iloc), GroupBy, Merge/Join | Completed |
| 010 | 10 Jun 2026 | Matplotlib Visualization | Completed |
| 011 | 11 Jun 2026 | Seaborn Visualization | Completed |
| 012 | 12 Jun 2026 | Statistics Foundations — Mean, Median, Variance, Distributions | Completed |
| 013 | 13 Jun 2026 | Probability & Bayes Theorem | Completed |
| 014 | 14 Jun 2026 | Linear Algebra Basics — Vectors, Matrices, Eigenvalues | Completed |
| 015 | 15 Jun 2026 | EDA Capstone — Full Exploratory Analysis Project | Completed |

# PHASE 02: REGRESSION + DEPLOYMENT

Day 016 - Day 029  |  16 Jun 2026 - 29 Jun 2026  |  Status: COMPLETED

| Day | Date | Topic | Status |
| --- | --- | --- | --- |
| 016 | 16 Jun 2026 | Simple Linear Regression — Theory & Math | Completed |
| 017 | 17 Jun 2026 | Simple Linear Regression — Implementation | Completed |
| 018 | 18 Jun 2026 | Multiple Linear Regression — Multicollinearity & VIF | Completed |
| 019 | 19 Jun 2026 | Polynomial Regression | Completed |
| 020 | 20 Jun 2026 | Gradient Descent — Batch, SGD, Mini-batch | Completed |
| 021 | 21 Jun 2026 | Regression Metrics — MSE, RMSE, MAE, R² | Completed |
| 022 | 22 Jun 2026 | Ridge Regression (L2) | Completed |
| 023 | 23 Jun 2026 | Lasso Regression (L1) & Elastic Net | Completed |
| 024 | 24 Jun 2026 | Feature Scaling for Regression | Completed |
| 025 | 25 Jun 2026 | Regression Project — Data Preprocessing (House Price) | Completed |
| 026 | 26 Jun 2026 | Regression Project — Model Training & Comparison | Completed |
| 027 | 27 Jun 2026 | Regression Project — Evaluation & Serialization | Completed |
| 028 | 28 Jun 2026 | Streamlit Basics for Deployment | Completed |
| 029 | 29 Jun 2026 | Deploy Regression Project (Streamlit Cloud) | Completed |

# PHASE 03: CLASSIFICATION FOUNDATIONS + LOGGING/PYTEST

Day 030 - Day 044  |  30 Jun 2026 - 14 Jul 2026  |  Status: ACTIVE

| Day | Date | Topic | Status |
| --- | --- | --- | --- |
| 030 | 30 Jun 2026 | Classification Project Architecture & Logging | Completed |
| 031 | 01 Jul 2026 | Pipeline Verification with Pytest | Current |
| 032 | 02 Jul 2026 | Sigmoid, Odds & Log-Odds | Upcoming |
| 033 | 03 Jul 2026 | Logistic Regression — Implementation | Upcoming |
| 034 | 04 Jul 2026 | Log Loss & Maximum Likelihood Intuition | Upcoming |
| 035 | 05 Jul 2026 | Multiclass Logistic Regression & Softmax | Upcoming |
| 036 | 06 Jul 2026 | Regularization in Logistic Regression (L1/L2, C parameter) | Upcoming |
| 037 | 07 Jul 2026 | Confusion Matrix, Accuracy, Type I/II Errors | Upcoming |
| 038 | 08 Jul 2026 | Precision, Recall & F1 Score | Upcoming |
| 039 | 09 Jul 2026 | ROC-AUC & PR-AUC Curves | Upcoming |
| 040 | 10 Jul 2026 | Decision Trees — Entropy & Gini Impurity | Upcoming |
| 041 | 11 Jul 2026 | Decision Trees — Information Gain & Splitting | Upcoming |
| 042 | 12 Jul 2026 | Decision Trees — Overfitting & Pruning | Upcoming |
| 043 | 13 Jul 2026 | Decision Tree Regressor + Visualization | Upcoming |
| 044 | 14 Jul 2026 | Classification Capstone — Loan Approval Full Pipeline + Tests | Upcoming |

# PHASE 04: ADVANCED PREPROCESSING + CORE CLASSIFIERS

Day 045 - Day 060  |  15 Jul 2026 - 30 Jul 2026  |  Status: UPCOMING

| Day | Date | Topic | Status |
| --- | --- | --- | --- |
| 045 | 15 Jul 2026 | SVM — Hyperplane & Margin | Upcoming |
| 046 | 16 Jul 2026 | SVM — Kernel Trick (Linear, RBF, Polynomial) | Upcoming |
| 047 | 17 Jul 2026 | SVM — Parameter Tuning (C, Gamma) | Upcoming |
| 048 | 18 Jul 2026 | Support Vector Regression (SVR) | Upcoming |
| 049 | 19 Jul 2026 | Naive Bayes — Theory & Bayes Theorem | Upcoming |
| 050 | 20 Jul 2026 | Naive Bayes — Gaussian / Multinomial / Bernoulli | Upcoming |
| 051 | 21 Jul 2026 | KNN — Core Algorithm & Distance Metrics | Upcoming |
| 052 | 22 Jul 2026 | KNN — K Selection & KNN Regressor | Upcoming |
| 053 | 23 Jul 2026 | Missing Value Imputation (Mean/Median/KNN/Iterative) | Upcoming |
| 054 | 24 Jul 2026 | Outlier Treatment (IQR, Z-score, Winsorization) | Upcoming |
| 055 | 25 Jul 2026 | Categorical Encoding Deep Dive | Upcoming |
| 056 | 26 Jul 2026 | Feature Scaling Deep Dive (Standard/MinMax/Robust) | Upcoming |
| 057 | 27 Jul 2026 | Feature Transformation (Log, Box-Cox, Yeo-Johnson) | Upcoming |
| 058 | 28 Jul 2026 | Feature Selection (Filter/Wrapper/Embedded Methods) | Upcoming |
| 059 | 29 Jul 2026 | sklearn ColumnTransformer & Pipelines | Upcoming |
| 060 | 30 Jul 2026 | Classifier Comparison Capstone Project | Upcoming |

# PHASE 05: ENSEMBLES, BOOSTING & UNSUPERVISED LEARNING

Day 061 - Day 082  |  31 Jul 2026 - 21 Aug 2026  |  Status: UPCOMING

| Day | Date | Topic | Status |
| --- | --- | --- | --- |
| 061 | 31 Jul 2026 | Bagging & Bootstrap Sampling | Upcoming |
| 062 | 01 Aug 2026 | Random Forest — Architecture | Upcoming |
| 063 | 02 Aug 2026 | Random Forest — Hyperparameters | Upcoming |
| 064 | 03 Aug 2026 | AdaBoost — Weak Learners & Weight Updates | Upcoming |
| 065 | 04 Aug 2026 | AdaBoost — Implementation | Upcoming |
| 066 | 05 Aug 2026 | Gradient Boosting — Mechanics | Upcoming |
| 067 | 06 Aug 2026 | Gradient Boosting — Implementation | Upcoming |
| 068 | 07 Aug 2026 | XGBoost — Math Intuition | Upcoming |
| 069 | 08 Aug 2026 | XGBoost — Hyperparameters | Upcoming |
| 070 | 09 Aug 2026 | XGBoost — Early Stopping & Missing Values | Upcoming |
| 071 | 10 Aug 2026 | XGBoost — Project | Upcoming |
| 072 | 11 Aug 2026 | LightGBM | Upcoming |
| 073 | 12 Aug 2026 | CatBoost | Upcoming |
| 074 | 13 Aug 2026 | Stacking Classifier/Regressor | Upcoming |
| 075 | 14 Aug 2026 | Voting Classifier/Regressor | Upcoming |
| 076 | 15 Aug 2026 | Ensemble Comparison Capstone Project | Upcoming |
| 077 | 16 Aug 2026 | K-Means Clustering | Upcoming |
| 078 | 17 Aug 2026 | K-Means — Elbow Method & Silhouette Score | Upcoming |
| 079 | 18 Aug 2026 | DBSCAN | Upcoming |
| 080 | 19 Aug 2026 | Hierarchical Clustering & Dendrograms | Upcoming |
| 081 | 20 Aug 2026 | PCA — Math & Implementation | Upcoming |
| 082 | 21 Aug 2026 | Clustering + PCA Capstone Project | Upcoming |

# PHASE 06: MODEL OPTIMIZATION + FASTAPI DEPLOYMENT

Day 083 - Day 095  |  22 Aug 2026 - 03 Sept 2026  |  Status: UPCOMING

| Day | Date | Topic | Status |
| --- | --- | --- | --- |
| 083 | 22 Aug 2026 | Cross Validation Strategies (K-Fold, Stratified) | Upcoming |
| 084 | 23 Aug 2026 | Bias-Variance Tradeoff | Upcoming |
| 085 | 24 Aug 2026 | Hyperparameter Tuning — GridSearch/RandomSearch | Upcoming |
| 086 | 25 Aug 2026 | Optuna for Hyperparameter Tuning | Upcoming |
| 087 | 26 Aug 2026 | Handling Imbalanced Data — SMOTE | Upcoming |
| 088 | 27 Aug 2026 | SHAP Values — Global/Local Interpretability | Upcoming |
| 089 | 28 Aug 2026 | LIME — Local Explanations | Upcoming |
| 090 | 29 Aug 2026 | FastAPI Basics — Path Operations, Pydantic | Upcoming |
| 091 | 30 Aug 2026 | FastAPI — Model Serving Endpoint | Upcoming |
| 092 | 31 Aug 2026 | Docker Basics — Dockerfile | Upcoming |
| 093 | 01 Sept 2026 | Docker — Containerizing an ML API | Upcoming |
| 094 | 02 Sept 2026 | ML Project — Fraud Detection (XGBoost + SMOTE + SHAP) | Upcoming |
| 095 | 03 Sept 2026 | Deploy Fraud Detection API (FastAPI + Docker) | Upcoming |

# PHASE 07: DEEP LEARNING FUNDAMENTALS + PYTORCH

Day 096 - Day 112  |  04 Sept 2026 - 20 Sept 2026  |  Status: UPCOMING

| Day | Date | Topic | Status |
| --- | --- | --- | --- |
| 096 | 04 Sept 2026 | Neural Network Basics — Perceptron | Upcoming |
| 097 | 05 Sept 2026 | Multi-Layer Perceptron (MLP) | Upcoming |
| 098 | 06 Sept 2026 | Forward Propagation from Scratch | Upcoming |
| 099 | 07 Sept 2026 | Backpropagation Math — Chain Rule | Upcoming |
| 100 | 08 Sept 2026 | Backpropagation — Implementation (NumPy) | Upcoming |
| 101 | 09 Sept 2026 | Activation Functions (Sigmoid, Tanh, ReLU family) | Upcoming |
| 102 | 10 Sept 2026 | Loss Functions (MSE, BCE, CCE) | Upcoming |
| 103 | 11 Sept 2026 | Optimizers — SGD, Momentum, RMSprop | Upcoming |
| 104 | 12 Sept 2026 | Optimizers — Adam, AdamW | Upcoming |
| 105 | 13 Sept 2026 | Regularization — Dropout, Batch Normalization | Upcoming |
| 106 | 14 Sept 2026 | Weight Initialization (Xavier, He) | Upcoming |
| 107 | 15 Sept 2026 | PyTorch — Tensors & Autograd | Upcoming |
| 108 | 16 Sept 2026 | PyTorch — nn.Module & Dataset/DataLoader | Upcoming |
| 109 | 17 Sept 2026 | PyTorch — Training Loop | Upcoming |
| 110 | 18 Sept 2026 | PyTorch — Model Serialization | Upcoming |
| 111 | 19 Sept 2026 | Learning Rate Schedulers | Upcoming |
| 112 | 20 Sept 2026 | MNIST Capstone (NumPy → PyTorch Comparison) | Upcoming |

# PHASE 08: COMPUTER VISION — CNNS & OPENCV

Day 113 - Day 128  |  21 Sept 2026 - 06 Oct 2026  |  Status: UPCOMING

| Day | Date | Topic | Status |
| --- | --- | --- | --- |
| 113 | 21 Sept 2026 | CNN Basics — Convolutions & Kernels | Upcoming |
| 114 | 22 Sept 2026 | CNN — Padding & Stride | Upcoming |
| 115 | 23 Sept 2026 | CNN — Pooling & Flattening | Upcoming |
| 116 | 24 Sept 2026 | CNN — Implementation in PyTorch | Upcoming |
| 117 | 25 Sept 2026 | Famous Architectures — LeNet, AlexNet, VGG | Upcoming |
| 118 | 26 Sept 2026 | Famous Architectures — ResNet, MobileNet | Upcoming |
| 119 | 27 Sept 2026 | Transfer Learning — Feature Extraction | Upcoming |
| 120 | 28 Sept 2026 | Transfer Learning — Fine-Tuning | Upcoming |
| 121 | 29 Sept 2026 | Data Augmentation | Upcoming |
| 122 | 30 Sept 2026 | Object Detection Concepts & YOLO | Upcoming |
| 123 | 01 Oct 2026 | YOLOv8 Custom Detection Project | Upcoming |
| 124 | 02 Oct 2026 | OpenCV Basics | Upcoming |
| 125 | 03 Oct 2026 | OpenCV Video Processing | Upcoming |
| 126 | 04 Oct 2026 | Image Segmentation & U-Net | Upcoming |
| 127 | 05 Oct 2026 | CV Capstone Project — Cat vs Dog / Emotion Detection | Upcoming |
| 128 | 06 Oct 2026 | CV Capstone — Deployment | Upcoming |

# PHASE 09: NLP & SEQUENCE MODELS

Day 129 - Day 143  |  07 Oct 2026 - 21 Oct 2026  |  Status: UPCOMING

| Day | Date | Topic | Status |
| --- | --- | --- | --- |
| 129 | 07 Oct 2026 | Text Preprocessing Pipeline | Upcoming |
| 130 | 08 Oct 2026 | Stemming vs Lemmatization | Upcoming |
| 131 | 09 Oct 2026 | Bag of Words (BoW) | Upcoming |
| 132 | 10 Oct 2026 | TF-IDF | Upcoming |
| 133 | 11 Oct 2026 | Word2Vec (CBOW & Skip-gram) | Upcoming |
| 134 | 12 Oct 2026 | GloVe & FastText | Upcoming |
| 135 | 13 Oct 2026 | RNN — Sequential Processing | Upcoming |
| 136 | 14 Oct 2026 | RNN — Vanishing Gradients | Upcoming |
| 137 | 15 Oct 2026 | LSTM Architecture | Upcoming |
| 138 | 16 Oct 2026 | GRU | Upcoming |
| 139 | 17 Oct 2026 | Bidirectional LSTM | Upcoming |
| 140 | 18 Oct 2026 | NLP Project — Sentiment Analysis (TF-IDF + ML) | Upcoming |
| 141 | 19 Oct 2026 | NLP Project — Sentiment Analysis (LSTM) | Upcoming |
| 142 | 20 Oct 2026 | Named Entity Recognition | Upcoming |
| 143 | 21 Oct 2026 | NLP Capstone — Resume Screener | Upcoming |

# PHASE 10: TRANSFORMERS, LLMS, RAG & AGENTS

Day 144 - Day 159  |  22 Oct 2026 - 06 Nov 2026  |  Status: UPCOMING

| Day | Date | Topic | Status |
| --- | --- | --- | --- |
| 144 | 22 Oct 2026 | Attention Mechanism | Upcoming |
| 145 | 23 Oct 2026 | Multi-Head Attention | Upcoming |
| 146 | 24 Oct 2026 | Transformer Encoder Block | Upcoming |
| 147 | 25 Oct 2026 | Transformer Decoder Block | Upcoming |
| 148 | 26 Oct 2026 | BERT — MLM & NSP | Upcoming |
| 149 | 27 Oct 2026 | BERT Variants & Fine-Tuning | Upcoming |
| 150 | 28 Oct 2026 | GPT Family & Causal Language Modeling | Upcoming |
| 151 | 29 Oct 2026 | Hugging Face Pipeline API | Upcoming |
| 152 | 30 Oct 2026 | Hugging Face AutoModel/AutoTokenizer + Fine-Tuning | Upcoming |
| 153 | 31 Oct 2026 | LLM Fundamentals — Tokens, Temperature, Top-P/K | Upcoming |
| 154 | 01 Nov 2026 | Prompt Engineering (Zero/Few-shot, Chain-of-Thought) | Upcoming |
| 155 | 02 Nov 2026 | LangChain Core Components | Upcoming |
| 156 | 03 Nov 2026 | Vector Databases (FAISS, ChromaDB) | Upcoming |
| 157 | 04 Nov 2026 | RAG Pipeline — Basic | Upcoming |
| 158 | 05 Nov 2026 | RAG Pipeline — Advanced (Hybrid Search, Re-ranking) | Upcoming |
| 159 | 06 Nov 2026 | AI Agents — LangGraph / CrewAI / MCP Introduction | Upcoming |

# PHASE 11: REACT / WEB FRONTEND

Day 160 - Day 168  |  07 Nov 2026 - 15 Nov 2026  |  Status: UPCOMING

| Day | Date | Topic | Status |
| --- | --- | --- | --- |
| 160 | 07 Nov 2026 | HTML/CSS/JS Refresher for React | Upcoming |
| 161 | 08 Nov 2026 | React Basics — Components, Props, State | Upcoming |
| 162 | 09 Nov 2026 | React Hooks (useState, useEffect) | Upcoming |
| 163 | 10 Nov 2026 | React — API Integration (fetch/axios) | Upcoming |
| 164 | 11 Nov 2026 | React — Forms & Routing | Upcoming |
| 165 | 12 Nov 2026 | Tailwind CSS for Styling | Upcoming |
| 166 | 13 Nov 2026 | Building an ML Model UI in React | Upcoming |
| 167 | 14 Nov 2026 | React State Management | Upcoming |
| 168 | 15 Nov 2026 | React Project — ML Dashboard Frontend | Upcoming |

# PHASE 12: FULL-STACK AI INTEGRATION

Day 169 - Day 175  |  16 Nov 2026 - 22 Nov 2026  |  Status: UPCOMING

| Day | Date | Topic | Status |
| --- | --- | --- | --- |
| 169 | 16 Nov 2026 | Connecting React Frontend to FastAPI Backend | Upcoming |
| 170 | 17 Nov 2026 | Full-Stack Auth Basics | Upcoming |
| 171 | 18 Nov 2026 | Full-Stack Project — Chat-with-PDF (RAG) UI | Upcoming |
| 172 | 19 Nov 2026 | Full-Stack Project — Backend Integration | Upcoming |
| 173 | 20 Nov 2026 | Full-Stack Project — Testing & Debugging | Upcoming |
| 174 | 21 Nov 2026 | Full-Stack Project — Deployment | Upcoming |
| 175 | 22 Nov 2026 | Full-Stack Capstone Review | Upcoming |

# PHASE 13: MLOPS & PRODUCTION PIPELINES

Day 176 - Day 187  |  23 Nov 2026 - 04 Dec 2026  |  Status: UPCOMING

| Day | Date | Topic | Status |
| --- | --- | --- | --- |
| 176 | 23 Nov 2026 | MLflow — Experiment Tracking | Upcoming |
| 177 | 24 Nov 2026 | MLflow — Model Registry | Upcoming |
| 178 | 25 Nov 2026 | DVC — Data Version Control | Upcoming |
| 179 | 26 Nov 2026 | GitHub Actions — CI/CD Basics | Upcoming |
| 180 | 27 Nov 2026 | GitHub Actions — Auto-Test Pipeline | Upcoming |
| 181 | 28 Nov 2026 | Monitoring — Evidently AI (Data Drift) | Upcoming |
| 182 | 29 Nov 2026 | Docker Compose — Multi-Container Apps | Upcoming |
| 183 | 30 Nov 2026 | AWS EC2 Basics | Upcoming |
| 184 | 01 Dec 2026 | AWS S3 for Model/Data Storage | Upcoming |
| 185 | 02 Dec 2026 | MLOps Pipeline Project — Setup | Upcoming |
| 186 | 03 Dec 2026 | MLOps Pipeline Project — Integration | Upcoming |
| 187 | 04 Dec 2026 | MLOps Pipeline Project — Full Deployment | Upcoming |

# PHASE 14: CAPSTONE DEVELOPMENT

Day 188 - Day 201  |  05 Dec 2026 - 18 Dec 2026  |  Status: UPCOMING

| Day | Date | Topic | Status |
| --- | --- | --- | --- |
| 188 | 05 Dec 2026 | Capstone — Idea Selection & Scoping | Upcoming |
| 189 | 06 Dec 2026 | Capstone — Data Collection | Upcoming |
| 190 | 07 Dec 2026 | Capstone — EDA | Upcoming |
| 191 | 08 Dec 2026 | Capstone — Feature Engineering | Upcoming |
| 192 | 09 Dec 2026 | Capstone — Model Building (v1) | Upcoming |
| 193 | 10 Dec 2026 | Capstone — Model Evaluation & Iteration | Upcoming |
| 194 | 11 Dec 2026 | Capstone — Model Building (v2 / Ensemble) | Upcoming |
| 195 | 12 Dec 2026 | Capstone — FastAPI Backend Build | Upcoming |
| 196 | 13 Dec 2026 | Capstone — React Frontend Build | Upcoming |
| 197 | 14 Dec 2026 | Capstone — Frontend-Backend Integration | Upcoming |
| 198 | 15 Dec 2026 | Capstone — Testing & Bug Fixing | Upcoming |
| 199 | 16 Dec 2026 | Capstone — Dockerization | Upcoming |
| 200 | 17 Dec 2026 | Capstone — Cloud Deployment | Upcoming |
| 201 | 18 Dec 2026 | Capstone — Documentation & Demo Video | Upcoming |

# PHASE 15: JOB READINESS & PORTFOLIO

Day 202 - Day 212  |  19 Dec 2026 - 29 Dec 2026  |  Status: UPCOMING

| Day | Date | Topic | Status |
| --- | --- | --- | --- |
| 202 | 19 Dec 2026 | GitHub Profile README | Upcoming |
| 203 | 20 Dec 2026 | Portfolio Website | Upcoming |
| 204 | 21 Dec 2026 | Resume Building (ATS-Optimized) | Upcoming |
| 205 | 22 Dec 2026 | LinkedIn Optimization | Upcoming |
| 206 | 23 Dec 2026 | SQL Basics + Joins | Upcoming |
| 207 | 24 Dec 2026 | SQL Window Functions + LeetCode SQL 50 | Upcoming |
| 208 | 25 Dec 2026 | ML Theory Interview Prep | Upcoming |
| 209 | 26 Dec 2026 | DL Theory Interview Prep | Upcoming |
| 210 | 27 Dec 2026 | ML System Design | Upcoming |
| 211 | 28 Dec 2026 | DSA Practice — Arrays through Trees (Problem Solving) | Upcoming |
| 212 | 29 Dec 2026 | Mock Interviews | Upcoming |

# PHASE 16: FINAL REVIEW

Day 213 - Day 214  |  30 Dec 2026 - 31 Dec 2026  |  Status: UPCOMING

| Day | Date | Topic | Status |
| --- | --- | --- | --- |
| 213 | 30 Dec 2026 | Full Roadmap Revision — Concept Recap | Upcoming |
| 214 | 31 Dec 2026 | Final Mock Interview + Application Strategy Launch | Upcoming |

# Final Deliverables by 31 December 2026

- 4 Classical ML Projects deployed (Titanic, Fraud Detection, Segmentation, Employee Churn)

- 1 PyTorch Deep Learning Project (MNIST, from-scratch + framework comparison)

- 1 Computer Vision Project (YOLOv8 Detection or U-Net Segmentation)

- 1 NLP Project (Resume Screener / Sentiment Analysis)

- 1 LLM/RAG/Agent Project (Chat-with-PDF or Multi-Agent System)

- 1 Full-Stack Capstone (React + FastAPI + Docker + Cloud Deployment)

- MLOps Evidence: MLflow runs, CI/CD pipeline, monitoring dashboard

- Job-Readiness: Resume, Portfolio site, LinkedIn, SQL 50, Mock Interviews

This roadmap is FINAL. It will not be rebuilt again — only followed, one day at a time.